## Over all Accounts
MUNSHI VILLA DUPLEX
SL.NO | DATE | REF. NAME | PURPOSE | TRANSPORT /LABOUR | BRICK (EIT) & BREAKING | CEMENT | ROD | SAND (BALI) | METARIALS | SOIL TEST & CUTTING | RAJMISTRI CONTRACTOR | OTHERS | HARDWARE | ELECTRIC | LABOUR |  | NOTE
25.02.2026
1 | 27.02.2026 | MOHSIN BOSS | YOUNUS MIA RAJMISTRICONTRACTOR) CONTRUCATIONS | [7 empty] | 15000
2 | 28.02.2026 | NAYEEM | MUNSHI BILLAH PROJECT SOIL TEST PURPOSE | [6 empty] | 15000
3 | 01-30.03.20226 | NAYEEM | MARCH MONTH OVERALL TA/DA ALLOWANCE PURPOSE | 2190
4 | 01.04.2026 | EMAN VAI | BRICK PURPOSE (ASIA BRICKS) |  | 200000 | [5 empty] | 70000
5 | 02.04.2026 | NAYEEM | YOUNUS MIA RAJMISTRICONTRACTOR) CONTRUCATIONS
6 | 04.04.2026 | EMAN VAI | BSRM ROD PURPOSE (HAJI ENTERPRISE) |  |  |  | 300000
7 | 05.04.2026 | RONY & EMAN VAI | RONY VAI IBBL A/C TRANSFER (ELECTRIC & OTHERS COST) | [8 empty] | 14000
8 | 06.04.2026 | EMAN VAI | EMAN VAI BIKASH NUMBER EMAN VAI (BALTI, BONDNA, TIRPARL OTHERS COSTING | [5 empty] | 3500
9 | 06.04.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE (RONY VAI TO EMAN VAI) BRICK BREAKING & OTHERS COST |  | 20000
10 | 06.04.2026 | RONY & EMAN VAI | SCREN CEMENT PURPOSE (HAJI ENTERPRISE) |  |  | 100000
11 | 09.04.2026 8 APR | RONY & EMAN VAI | SCREN CEMENT PURPOSE (HAJI ENTERPRISE) |  |  | 104500
12 | 14.04, 16.04. 2026 | EMAN VAI | MUSHI BILLAH SITE- COSTIGN GIVEN UPDATE EMAN VAI (COSTING FROM MUNSHI) YOUNUS CONTRACTOR=16K, BAKU BILL=20K, DRAM & LAYBOR SNACK=300 | 300 | [5 empty] | 20000 | 16000
13 | 19.04.2026 | RONY & EMAN VAI | BALI & SELECTIONS PURPOSE HALAL ENTERPRISE |  |  |  |  | 50000
| 20.04.2026 | AZIZUL VAI | DAILY COST (AZIZUL VAI MUNSHI BILLAH SITE VISIT PURPOSE) | 1000
14 | 20.04.2026 | NAYEEM | YOUNUS MIA RAJMISTRICONTRACTOR) CONTRUCATIONS | [7 empty] | 70000
15 | 21.04.2026 | EMAN VAI | TUNKY SOIL CUTTING PURPOSE (LABOUR) | [11 empty] | 5680
| 21.04.2026 | EMAN VAI | DAILY ALLOWANCE PURPOSE ADVANCE EMAN VAI | 2000
16 | 25.04.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE HALAL ENTERPRISE (DUE BALANCE TRANSFER) SAND |  |  |  |  | 30000
17 | 25.04.2026 | EMAN VAI | MUNSHI BILLAH SITE (NAIL) PERAK PURPOSE | [9 empty] | 2200
18 | 26.04.2026 | NAYEEM | MUNSHI BILLAH PROJECT (YOUNUS MIA CONTRACTOR) CONTRUCATIONS | [7 empty] | 50000
19 | 03.05.2026 | EMAN VAI | MUNSHI BILLAH PROJECT- CONSTRUCATIONS MATERIALS (MISTRI BAY COST PAID) | [5 empty] | 2650
20 | 01.04 -30.04.2026 | NAYEEM | APRIL MONT (EMAN, IMRNA, RONY, AZIZUL VAI ) TA/DA COST | 5470
21 | 03.05.2026 | NAYEEM | MUNSHI BILLAH PROJECT- EMAN VAI MARCH MONTH TA/DA COST | 4000
22 | 04.05.2026 | RONY & EMAN VAI | MUNSHI BILLAL SITE- HALAL ENTERPRISE (BALI) DUE BALANCE |  |  |  |  | 20000
23 | 05.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- SAND (BALI) PURPOSE (3RD PARTY) |  |  |  |  | 38000
24 | 05.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- SCRAN CEMENT PURPOSE (HALAL ENTERPRISE) |  |  | 50000
25 | 06.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- SOIL CUTTING PURPOSE (BAKU) CHARGE | [6 empty] | 22000
26 | 06.05.2026 | EMAN VAI | MUNSHI BILLAH SITE- BIT BORAT PURPOSE LAYBOR BILL | [8 empty] | 4000
27 | 06.05.2026 | EMAN VAI | MUNSHI BILLAH SITE- PATER BOSTHA & NAIL (TARKATA) | [9 empty] | 4000
28 | 07.05.2026 | NAYEEM | MUNSHI BILLAH SITE- EMAN VAI DAILY ALLOWANCE | 2000
29 | 10.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- HALAL ENTERPRISE (PREVIOUE DUE & NEW BALI PAYMENT) |  |  |  |  | 50000
30 | 12.05.2026 | NAYEEM | MUNSHI BILLAH SITE- YOUNUS CONTRACTOR | [7 empty] | 50000
31 | 13.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- HALAL ENTERPRISE (BSRM ROAD PAYMENT) |  |  |  | 70000
32 | 16.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH PROJECT-PIVE FILTER MATARIALS PURPOSE | [9 empty] | 7530
33 | 16.05.2026 | EMAN VAI | MUNSHI BILLAH PROJECT- EMAN VAI PREVIOUS ALLOWANCE, NEW ALLOWANCE | 3470
34 | 22.05.2026 | RONY & EMAN VAI | MUNSHI BILLAH SITE- BALI (SAND) TRANSFORT LABOUR BILL (BIT BORAT) | [11 empty] | 8000
35 | 25.05.2026 | NAYEEM | YOUNUS CONTRACTOR (TALIM HOSSAIN BKASH) | [7 empty] | 10000
36 | 01.05 -31.04.2026 | NAYEEM | APRIL MONT (EMAN, IMRNA, RONY, AZIZUL VAI ) TA/DA COST | 1000
37 | 09.0.06.2026 | TALIM VAI BKASH | LAYBOUR BILL (TALIM) | [11 empty] | 6900
38 | 11.06.2026 | TALIM VAI BKASH | TARKATA PURPOSE (TALIM BHAI BKASH) | [9 empty] | 1120
39 | 13.06.2026 | BOSS TO TALIM VAI BKASH | TARKATA PURPOSE | [9 empty] | 2140
40 | [16 empty] | UPDATED
41 | 21.06.2026 | RONY VAI | ROD PURPOSE (HAJI ENTER PRISE |  |  |  | 150000
42 | 21.06.2026 | RONY VAI | HARDWARE METARIALS PURPOSE | [9 empty] | 7000
43 | 21.06.2026 | RONY VAI | BSRM ROD PURPOSE (16mm= 1402.3 Kg, 12 mm=356.2 Kg, 8mm= 504.5 Kg) With Labour Fee (HAJI ENTERPRISE) |  |  |  | 216550
44 | 23.06.2026 | RONY VAI | BSRM ROD PURPOSE ( 10mm= 1398KG, RING 50 PCS) With Labour Fee (HAJI ENTERPRISE) |  |  |  | 135177
45 | 27.06.2026 | RONY VAI | BSRM ROD PURPOSE (16mm= 75KG, 12mm= 170 Kg, 10mm= 149 kg) With Labour & Van bara (HAJI ENTERPRISE) |  |  |  | 37925
46
47
48
49
50
51
52
53
54
55
56
57
58
|  |  | PROJECT COSTING PURPOSE COST BALANCE | 21430 | 220000 | 254500 | 909652 | 188000 | 6150 | 57000 | 281000 | 18000 | 23990 | 0 | 20580 | 0
PROJECT COSTING PURPOSE BUDGET BALANCE
|  |  | PROJECT COSTING PURPOSE RE-MAINING BALANCE | -21430 | -220000 | -254500 | -909652 | -188000 | -6150 | -57000 | -281000 | -18000 | -23990 | 0 | -20580 | 0
|  |  | DUE BALANCE - (ASIA BRICKS= 160K, & HALAL ENTERPRISE= 58148) | 281898
|  |  | TOTAL COST | 2282200
COSTING BUDGET
RE-MAINING DUE COST BALANCE
|  |  | Project Value | 7000000
|  | 12.03.2026 | 1st Payment Received | -1000000
|  | 01.04.2026 | 2nd Payment Received | -2000000
|  | 11.05.2026 | 3rd Payment Received | -1000000
|  |  | RE-MAINING DUE BALANCE | 3000000

## Over All Cost Summary
Munshi Villa-Duplex- Overall summary
SL | Purpose | Cost | Budget
1 | Bricks & Breaking | 414000
2 | Cement | 273780
3 | Sand/Bali | 244920
4 | Rod | 856397
5 | Hardware | 24160
6 | Sanitary | 7530 | 4,00,000
7 | Soil Excavation & Fill | 59980
8 | Electrical | 22800 | 3,50,000
9 | 3D Design office | 30000 | 50000
10 | Transport & Visit | 43790 | 1,00,000
11 | Extra Labour | 16300
12 | Younus Contactor | 341000 | 13,44,000
13 | Extra/Others Bill | 13600 | 90215
14 | Tiles Work
15 | Paint
16 | Metal
17 | Aluminium
18 | Wood Work
2348257
Note-Due
| Asia Bricks Purpose Due | 160000
| Helal Enterprise Sand Purpose Due | 73198
| HAJI ENTERPRISE (ROD) | 135552
368750
Up to - 09.07.2026

## Sheet22
Munshi Villa-Duplex- Overall summary
SL | Purpose | Cost | Budget
1 | Bricks & Breaking | 414000
2 | Cement | 273780
3 | Sand/Bali | 255000
4 | Rod | 856397
5 | Hardware | 24160
6 | Sanitary | 7530 | 4,00,000
7 | Soil Excavation & Fill | 59980
8 | Electrical | 22800 | 3,50,000
9 | 3D Design office | 30000 | 50000
10 | Transport & Visit | 40790 | 1,00,000
11 | Extra Labour | 16300
12 | Younus Contactor | 341000 | 13,44,000
13 | Extra/Others Bill | 13600 | 90215
14 | Tiles Work
15 | Paint
16 | Metal
17 | Aluminium
18 | Wood Work
2355337
Note-Due
| Asia Bricks Purpose Due | 160000
| Helal Enterprise Sand Purpose Due | 73198
| HAJI ENTERPRISE (ROD) | 135552
| TALIM HARDWARE & LABOUR | 2160
370910
09.07.2026 Porjonto Hisabe

## Bricks & Breaking
Bricks & Breaking
SL | Date | Description | Quantity | Rate Per Bricks | Taka | NOTE
1 | 31.03.2026 | Asia Bricks - 1 Number | 4000 | 12 | 48000
2 | 01.04.2026 | Asia Bricks - 1 Number | 16000 | 12 | 192000
3 | 02.04.2026 | Asia Bricks - For Precket Breaking | 10000 | 12 | 120000
6 | 06.14.2026 | 10K BRICKS BREAKING PURPOSE |  |  | 12600
7 | 27.06.2026 | 3K BRICKS BUY & BREAKING PURPOSE (HALAL) | 3000 |  | 41400
8
9
10
11
|  |  | 33000 |  | 414000

## Cement
Cement
SL | Date | Details | Quantity | Rate | Total Taka | Paid Taka | Due Or Advance
| 06.04.2026 | Cement Purpose -Scan Cement | 200 Bags | 535 | 108000
| 05.05.2026 | Cement Purpose -Scan Cement | 100 Bags | 535 | 54000
|  | Cement Purpose -Scan Cement (HALAL) | 07 BAGS |  | 3780
|  | Cement Purpose -Scan Cement | 200 Bags |  | 108000
273780

## Rod
Rod
SL.N | Date | Details | Quantity | Amount | TOTAL AMOUN | NOTE
1 | 04.04.2026 | BSRM ROD PURPOSE ( 16mm= 3200 kg, 8 mm= 500 kg, 12mm 200kg, 10mm 10 peice) with labour (HAJI ENTERPRISE) |  | 396695 | 396695
2 | 12.05.2026 | BSRM ROD PURPOSE( 8mm= 1984KG, 10mm= 4955KG) with labour (HALAL ENTERPRISE) |  | 70000 | 466695
3 | 21.06.2026 | BSRM ROD PURPOSE (16mm= 1402.3 Kg, 12 mm=356.2 Kg, 8mm= 504.5 Kg) With Labour Fee (HAJI ENTERPRISE) | 2263 KG | 216550 | 683245
4 | 23.06.2026 | BSRM ROD PURPOSE ( 10mm= 1398KG, RING 50 PCS) With Labour Fee (HAJI ENTERPRISE) | 1398KG & 50 PCS | 135177 | 818422
5 | 27.06.2026 | BSRM ROD PURPOSE (16mm= 75KG, 12mm= 170 Kg, 10mm= 149 kg) With Labour & Van bara (HAJI ENTERPRISE) | 395 KG | 37925 | 856347
6

## SandBali
Sand/Bali
15.04.2026 | Selection Bali- Helal Enterprise | 650 FEET | 93000
15.04.2026 | WHITE BALI- HALAL ENTERPRISE | 600 FEET | 46500
25.04.2026 | RED BALI- HALAL ENTERPRISE | 200 FEET | 17000
05.05.2026 | WHITE BALI- HALAL ENTERPRISE | 300 FEET | 6900
05.05.2026 | RED BALI (3DR PARTY)
08.05.2026 | RED BALI- HALAL ENTERPRISE | 300 FEET | 6900
11.05.2026 | BIT BALI- HALAL ENTERPRISE | 1200 FEET | 28000
13.05.2026 | BIT BALI- HALAL ENTERPRISE | 600 FEET | 13800
15.05.2026 | BIT BALI- HALAL ENTERPRISE | 400 FEET | 9200
15000
11200
7500
255000

## HARDWARE
Hardware MATERIALS
SL | DATE | REF. NAME | PURPOSE DETAILS | QUANTITY | AMOUNT | TOTAL AMOUNT | TRANS. TYPE | NOTE
1 | 06.04.2026 | EMAN VAI | EMAN VAI BKASH NUMBER EMAN VAI (BALTI, BODNA, TIRPAL OTHERS COSTING |  | 6940 | 6940
2 | 25.04.2026 | EMAN VAI | TARKATA PURPOSE |  | 2200 | 9140
3 | 06.05.2026 | EMAN VAI | PATER BOSTHA & NAIL (TARKATA) |  | 4000 | 13140
4 | 11.06.2026 | RONY & EMAN VAI | TARKATA PURPOSE |  | 1120 | 14260
5 | 13.06.2026 | TALIM VAI | TARKATA PURPOSE |  | 2140 | 16400
| 21.06.2026 | BOSS & RONY VAI | HARDWARE MATERIALS |  | 7000 | 23400 | BKASH TRANSFER
| 02.07.2026 | TALIM VAI |  |  | 760 | 24160 | DUE

## Sanitary
Sanitary
SL | Date | Details
| 16.05.2026 | Sanitary Products- Pipe Filter | 7530

## Soil Excavation & Fill
Soil Excavation & Fill
14.04.2026 | BEKU BILL (MATI KATA) | 20000
06.05.2026 | BEKU BILL (MATI BHORAT) | 22000
06.05.2026 | LOBOUR BILL MATI BORAT | 4000
20.04.2026 | BIT BHORAT (BALI) | 5680
51680

## Electrical
Electrical- Meterials
SL | Date | Details
05.04.2026 | RONY & EMAN VAI | ELECTRIC MATERIALS & OTHERS COST) | 14000
29.06.2026 | RONY VAI | ELECTRIC MATERIALS PRUPOSE (BAYATOLLA ELECTRONICS) | 8800
22800

## 3D Design office
Office Design Purpose
| 3D Design Purpose Office Cost | 30000

## Transport & Visit
Transport
| 05.02.2026 |  | 1st Visit For Land Observation | 3000 | 3000
| 03.03.2026 |  | 2nd Visit Meserment | 2000 | 5000
| 10.03.2026 |  | 3rd visit Soil test | 2000 | 7000
| 01.04.2026 |  | 4th visit Before Work Finalize | 3000 | 10000
| 20.04.2026 | AZIZUL VAI | DAILY COST (AZIZUL VAI MUNSHI BILLAH SITE VISIT PURPOSE) | 1000 | 11000
| 21.04.2026 | EMAN VAI | DAILY ALLOWNANCE PURPOSE ADV. EMAN VAI | 2000 | 13000
| 26.04.2026 |  | 5th visit For work verify | 2000 | 15000
| 05.05.2026 |  | 6th visit For work verify | 2000 | 17000
| 18.05.2026 |  | 57th visit For work verify | 2000 | 19000
| 13.06.2026 |  | 7th visit For Plan Correction & Verify Work | 2000 | 21000
| 01-30.03.20226 | NAYEEM | MARCH MONTH OVERALL TA/DA ALLOWANCE PURPOSE | 2190 | 23190
| 06.04.2026 | EMAN VAI | EMAN VAI MATERIALS DELIVERY PURPOSE | 460 | 23650
| 14.04, 16.04. 2026 | EMAN VAI | COSTIGN GIVEN UPDATE EMAN VAI (COSTING FROM MUNSHI) YOUNUS CONTRACTOR=16K, BAKU BILL=20K, DRAM & LAYBOR SNACK=300 | 300 | 23950
| 01.04 -30.04.2026 | NAYEEM | APRIL MONTH (EMAN, IMRNA, RONY, AZIZUL VAI ) TA/DA COST | 5470 | 29420
| 03.05.2026 | NAYEEM | EMAN VAI MARCH MONTH TA/DA COST | 4000 | 33420
| 07.05.2026 | NAYEEM | EMAN VAI DAILY ALLOWANCE | 2000 | 35420
| 16.05.2026 | EMAN VAI | EMAN VAI PREVIOUS ALLOWANCE, NEW ALLOWANCE | 3470 | 38890
| 01.05 -31.04.2026 | NAYEEM | MAY MONTH (EMAN, IMRNA, RONY, AZIZUL VAI ) TA/DA COST | 1000 | 39890
|  |  | RONY VAI | 2000 | 41890
| 01.06 -30.06.2026 |  | JUNE MONTH (EMAN, IMRNA, RONY, AZIZUL VAI ) TA/DA COST | 1900 | 43790

## Extra Labour
Extra Labour
SL | Date | Details
| 22.05.2026 | BIT BHORAT (BALI) | 8000
| 09.06.2026 | BIT BHORAT (BALI) | 6900
|  | BEKU BILL (MATI BHORAT) | 1400
16300

## Younus Contactor
Younus Contactor
SL | Date | Purpose |  | Given Amount | Total Given Amount
| 27.02.2026 | BANK TRASFER | EPAL TRAVELS IBBL TO YOUNUS MIA IBBL A/C | 15000 |  | Soil Test Purpose | Soil Test,Structural,Quotation Budget
| 02.04.2026 | BANK TRASFER | EPAL IT BRAC TO YOUNUS MIA IBBL A/C | 70000
| 14.04.2026 | CASH | MUNSHI GIVEN TO YOUNUS CONTRACTOR | 16000
| 20.04.2026 | BANK TRASFER | EMI IBBL TO YOUNUS MIA IBBL A/C | 70000
| 26.04.2026 | BANK TRASFER | EMI IBBL TO YOUNUS MIA IBBL A/C | 50000
| 12.05.2026 | BANK TRASFER | EMI IBBL TO YOUNUS MIA IBBL A/C | 50000
| 25.05.2026 | TALIM BAKSAH | MOHSIN BOSS TO TALIM BKAH | 10000
| 26.06.2026 | TALIM BAKSAH | MOHSIN BOSS TO TALIM BKAH | 10000
| 29.06.2026 | BANK TRASFER | EPAL TRAVELS DBL TO YOUNUS MIA IBBL A/C | 40000
10000
341000

## ExtraOthers Bill
Extra/Others Bill
SL | Date | Details
1 | 06.04.2026 | EMAN VAI BIKASH NUMBER EMAN VAI (BALTI, BONDNA, TIRPARL OTHERS COSTING | 3500
2 |  | MUNSHI BILLAH PROJECT- CONSTRUCATIONS MATERIALS (MISTRI BAY COST PAID) | 2650
| 15.04.2026 | CAMICEL | 1400
|  | MUNSHI BILLAH SITE- DALAI PURPOSE POLYTHINE | 2000
|  | CAMICEL | 4050
13600